## Sheet1
Phase |  | When found | status | Fix Time | Summary | Link | Done Low (days) | Done High (days) | Low (days) | High (days) | Issue Type | Reporter | Resolution | Deferrable | Comments
|  | Pre Review 1 | done | 0 | Type conflict when using old model as custom model with new reportgen_xxx.seq files | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324726&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.2 | 2 | 0 | 0 | User Misunderstanding? | daniel | closed - not a bug | yes
|  | Pre Review 1 | done | 0.2 | New process model code is modifying shared step settings for sequences that could potentially be run in parallel | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324976&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.2 | 0.5 | 0 | 0 | New | doug | Fixed
|  | Pre Review 1 | done | 0.1 | Result Processing dialog sometimes disappears for no apparent reason | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=326105&SAVE_DRAFT=N&TIMESTAMP=1322765240711&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 5 | 0 | 0 | New | Jed |  |  | not currently reproducible - only seen by Jed
|  | Pre Review 1 | done | 3 | Can't cut or copy text in Result Processing Dialog box | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324964&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.5 | 1.5 | 0 | 0 | New | James |  | if emergency | consequence of using CVI hot keys… may need to implement hot keys manually. Not sure about table control support for text operations.
|  | Pre Review 1 | done | 0.2 | Sequence Editor freezes when running Test UUTs entry point in batch model if two result processing configurations are enabled | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=326890&ID_CACHE_NAME=Pluto_p40108189_31674 | 1 | 3 | 0 | 0 | New | Magus | resassigned to Jimmy (expression deadlock)
|  | Pre Review 1 | done | 0.8 | Parallel Model Repeatedly Overwrites The Same Report File, Losing All Data But Last UUT | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324437&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.3 | 1.5 | 0 | 0 | New | Jed | Needed to pass configs by ref to post uut for new threads
|  | Pre Review 1 | done | 1 | Callbacks have changed order, some callbacks are not called in new models | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324452&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.3 | 1.5 | 0 | 0 | New | Magus |  | if emergency | For more rigorous backward compatibility
|  | Pre Review 1 | done | 1.3 | offline result processing - clearing the inbox while parallel model (and probably all other models too) are running results in runtime errors in the executions | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327025&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.2 | 1.5 | 0 | 0 | New | Doug
|  | Pre Review 1 | done | 0.2 | offline result processing - parallel model reports only show the last UUT's report even when result file had results from multiple UUTs | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327021&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.3 | 1.5 | 0 | 0 | New | Doug | duplicate
|  | Pre Review 1 | done | 0.8 | Store oldest version of TestStand that can open TSR files in the TSR header | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=323981&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.2 | 1 | 0 | 0 | New (Deferred Task) | James
|  | Pre Review 1 | done | 0.1 | Standard Process Model Callbacks Should Have Consistent Signatures (PreUUT/PostUUT) | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324740&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 0.6 | 0 | 0 | Preexisting | Jed | fixed as part of another car
|  | Pre Review 1 | done | 0.6 | Make the "Copy Steps and Locals when Creating an Overriding Sequence" option checked default | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=212695&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.5 | 2 | 0 | 0 | Preexisting | Manooch
|  | Pre Review 1 | done | 0.1 | Review 4.0 fix for when a menu is showing and you exit a UI, you can get property object leaks or an access violation | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=49761&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.5 | 5 | 0 | 0 | Preexisting | Jimmy |  | yes | Old UI CAR for obscure weird issue with menus. Unrelated to anything recent.
|  | Pre Review 1 | done | 0.02 | [Automated Test] Return Value in member 'GetProfilerWindow' fails when writing to a variable of type 'Number' | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=319678&SAVE_DRAFT=N&TIMESTAMP=1322758779878&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0.2 | 0.6 | 0 | 0 | Testplan | Jimmy | reassigned to Jimmy
|  | Pre Review 1 | done | 0.02 | API Hole, no way to opt out of the global go to cleanup option | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=224784&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 0.3 | 0 | 0 | Testplan | Jimmy | Fixed | yes | now just an automated test nitpick
|  | Pre Review 1 | done | 0.3 | Move exported result processing API from resultprocessing.c to a header file | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324841&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.3 | 1 | 0 | 0 | Usability/Cosmetic | James
|  | Pre Review 1 | done | 1.1 | Processing with an invalid plugin finishes successfully | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324286&SAVE_DRAFT=N&TIMESTAMP=1322757918663&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0.5 | 2 | 0 | 0 | Usability/Cosmetic | Magus |  | if emergency
|  | Pre Review 1 | done | 0.3 | NI_ReportGenerator.seq has expression error in file global variable | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324580&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 0.3 | 0 | 0 | Usability/Cosmetic | Jeff |  |  | Not an error, but using #novalidation would be nice
|  | Pre Review 1 | done | 1.2 | TS 2012 Process Models can error with a type conflict | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=316242&ID_CACHE_NAME=Pluto_p40108189_31674 | 1 | 2 | 0 | 0 | Usability/Cosmetic | Jeff |  | if emergency
|  | Pre Review 1 | done | 0.2 | Result Processing configuration dialog is too laggy/unresponsive | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324404&SAVE_DRAFT=N&TIMESTAMP=1322765943669&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0.5 | 10 | 0 | 0 | Usability/Cosmetic | Jeff |  | if emergency | reported on a specific old machine, not sure if it happens anywhere else
|  | Pre Review 1 | done | 1 | Selection jumps unexpectedly in result processing configuration dialog | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324409&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.3 | 1 | 0 | 0 | Usability/Cosmetic | Jeff |  | if emergency
|  | Pre Review 1 | done | 1.7 | Issues found in result processing dialog | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=325317&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.5 | 2 | 0 | 0 | Usability/Cosmetic (Mostly) | Sahana |  | if emergency
|  | Pre Review 1 | done | 0 | [Review] The Deployment Utility should allow users to select only some result processing configurations to deploy | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324818&SAVE_DRAFT=N&TIMESTAMP=1322766193763&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 10 | 0 | 0 | Usability/Cosmetic | magus | reassigned to scott for deferral | yes | I favor rejecting this
|  | Post Review 1 | done | 0.8 | Report list files should store a unique identifier of the TSR that generated them and they should not process if they are paired with another TSR | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327838 | 2 | 2 | 0 | 0 | Feature Enhancement Idea | magus | Implemented
|  | Post Review 1 | done | 0.2 | Positive ParentId values passed to OTF model plug-in callback for main sequence callback for new executions in a model | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327827 | 1 | 1 | 0 | 0 | User Misunderstanding? | Jed | Closed - Not a bug
|  | Post Review 1 | done | 0.5 | Model Plugin - Initialize" callback to the plug-in architecture | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327969 | 1 | 2 | 0 | 0 | Feature Enhancement Idea | jed
|  | Post Review 1 | done | 0.8 | Change for Semiconductor breaks deserialization assumptions | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=330163 | 1 | 3 | 0 | 0 | Tester OS Changes | James | Fixed
|  | Post Review 1 | done | 0.6 | Investigate Performance of Post UUT due to extra parameters | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=330131 | 0.1 | 1 | 0 | 0 | Tester OS Changes | Allen
|  | Post Review 1 | done | 0.3 | Prefix ResultLog methods with "Log" to verb-ize them. | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=331224 | 0.3 | 1 | 0 | 0 | API Review Feedback | Jimmy
|  | Post Review 1 | done | 0.2 | ModelOptions callback not working for ModelOptions.NumTestSockets in ModelSupport.seq | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332076 | 0.2 | 0.2 | 0 | 0 | New | Jed
|  | Post Review 1 | done | 0.5 | When splitting UUTs Offline Results plugin is creating files with the same name as files it had previously created | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332428 | 0.2 | 1 | 0 | 0 | New | magus
|  | Post Review 1 | done | 0.2 | [Investigate] Pure virtual function call likely caused by race condition in modelsupport2.dll | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332019&IS_EMBEDDED_PAGE=N | 0.2 | 0.6 | 0 | 0 | Not reproducible | jed
|  | Post Review 1 | done | 0.4 | <Batch> macro does not work for "Test UUTs" | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332469 | 0.2 | 0.6 | 0 | 0 | Tester OS Changes | jed
|  | Pre Review 1 |  | 0.2 | Attached config file leads to CVI memory corruption warning when converting objhandle to interface | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=326958&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 0 | 5 | ?? | anand | reassigned to magus |  | not currently reproducible … might be a CVI compiler issue
|  | Pre Review 1 |  |  | Aborting/terminating process models doesn't work in cases it used to | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=325166&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 3 | Half Prexisting/Half New | Jimmy
|  | Pre Review 1 |  |  | Database Options dialog box when opened after install does not default to a connection string that would operate on the Access database in the Public directory | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324219&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 0.2 | 1 | New | Scott
|  | Pre Review 1 |  |  | offline result processing - terminating or aborting executings when using parallel model (probably others too) results in runtime errors in process models | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=327029&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 2 | 5 | New | Doug
|  | Pre Review 1 |  |  | DynamicClientSequenceFile example reports run-time error when run in TS 2012 |  | 0 | 0 | 0.5 | 6 | New (Deferred Task) | Erik |  | if emergency | CAR is for fixing a horribly kludged example. The best fix might take a few days, but would be very good for Tester OS and the Model Plugin architecture
|  | Pre Review 1 |  |  | Getting deadlock when using two database loggers | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=325123&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 4 | Preexisting | jose
|  | Pre Review 1 |  |  | [Review] Determine if we need way to get report path more easily from callbacks | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=321070&SAVE_DRAFT=N&TIMESTAMP=1322768808864&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 0 | 0.5 | 4 | Preexisting | Erik |  |  | Preexisting issue made worse because the new models prevent a previous kludge that could work around it
|  | Pre Review 1 |  |  | Getting duplicate values error when using OTF and Non-OTF database loggers not running in a new thread | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324587&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 5 | Preexisting (maybe) | Jose
|  | Pre Review 1 |  |  | Usability feedback - Modify existing report plugin test plan | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324893&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 2 | 11 | Usability/Cosmetic | Jeff
|  | Pre Review 1 |  | 1 | Usability Suggestions for Results Processing | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324450&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 3 | Usability/Cosmetic | rick
|  | Pre Review 1 |  | 4 | Bugs and usability issues for Result Processing feature | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324846&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 4 | 8 | New and Usability/Cosmetic | Doug
|  | Post Review 1 |  | 0.1 | Ensure that Reserializer enforces PostUUT for test sockets executes before batch controller | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=330130 | 3 | 5 | 0 | 0 | Tester OS Changes | Allen
|  | Post Review 1 |  | 0 | Executing sequence file using Batch model with given Result processing configuration file hangs | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332933&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 0.5 | 0 | 0 | Tester OS Changes | Shashidhar Setty |  |  | duplicate
|  | Post Review 1 |  | 0.6 | Reset to Defaults in "Result Processing" dialog gives error box complaining of NULL FilleGlobals | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332957&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 1 | 0 | 0 |  | jed
|  | Post Review 1 |  | 1 | Report plugin causes executions using batch model to hang or deadlock | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332567&ID_CACHE_NAME=Pluto_p40108189_31674 | 0.1 | 0.5 | 0 | 0 | Tester OS Changes | erik
|  | Post Review 1 |  | 3 | Change Model Plugin - PreUUT/PostUUT to Model Plugin - PreBatch/PostBatch for batch controller thread | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=333221 | 1 | 2 | 0 | 0 | Usability/Cosmetic | doug
|  |  |  | 0.4 | Somehow the non-deletable default configurations are now deletable | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=333209 | 0.1 | 0.4 | 0 | 0 |  | james
[5 empty] | Offline results (.tsr) files need a way to convert times in results to absolute time. | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=333927 |  |  | 0.5 | 1 |  | jed
[5 empty] | Offline result processors in the offline configuration are not being ignored like it says they are supposed to be | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=326663&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | doug
[5 empty] | [Review] [Automated Test] Termination status reporting issues | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=224640&ID_CACHE_NAME=Pluto_p40108189_31674
[5 empty] | [Review] Offline results (.tsr) files need a way to convert times in results to absolute time. | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=333927&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | jed
|  |  |  | 0.25 | Test UUTs for Batch model creates an extra set of empty batch and UUT report files | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=334040&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | Megha Boggaram
|  |  |  | 0.6 | Consider calling Model Plugin - Initialize for disabled plugins and move report and database options callbacks to be invoked from Iniitialize | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=334417&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | james
|  |  |  | 0.1 | Simple Text report loses steps from report for the last batch | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=334376&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | james
[5 empty] | [Automated Test] Failure in test: 'Types that MUST not be Editable types' - type NI_SequentialTestSocket is editable. | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=333370&ID_CACHE_NAME=Pluto_p40108189_31674
|  |  |  | 0.5 | Persistence Tester test sequence errors out with 'Operation Failed' error when calling 'ResultLogger.LogEnd' with Batch process model using the Test UUTs entry point | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=329768&ID_CACHE_NAME=Pluto_p40108189_31674
|  |  |  | 0.1 | Offline Results Generator structures inconsistently named. | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=334150&ID_CACHE_NAME=Pluto_p40108189_31674 | [5 empty] | jed
[5 empty] | TSR files need a new GUID when they split | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=335902
|  |  |  | 25.64 |  |  |  |  | 13.7 | 55
|  | Pre Review 1 |  |  | Documentation updates for Result Processing feature | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=326461&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 8 | 25 | Documentation | Scott
|  | Pre Review 1 |  |  | Release Notes Reminders | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=309391&SAVE_DRAFT=N&TIMESTAMP=1322765543290&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 0 | 0.1 | 0.3 | Documentation | James
Beta1 |  | Post Review 1 |  |  | Numerous bugs and non-standard code in model swapping code in teststandservice | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=332852&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 0.3 | 1 | New | doug
Beta1 |  | Pre Review 1 |  |  | Can't recreate a plugin if you delete it from the file system while the Result Processing dialog box is up | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=314720&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 3 | Usability/Cosmetic | James |  | yes
Beta1 |  | Pre Review 1 |  |  | Logging to database is very slow when using two loggers and one of them is running in a new thread | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324591&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 1 | 10 | Preexisting (maybe) | Jose
Beta1 |  | Pre Review 1 |  |  | Decide whether result processing should be asynch by default | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=304782&ID_CACHE_NAME=Pluto_p40108189_31674 | 0 | 0 | 0.1 | 0.5 | New (Deferred Task) | James
Beta1 |  | Pre Review 1 |  |  | Action items from result processing spec review meeting -Document issues with writing to network for both report/database | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=320046&SAVE_DRAFT=N&TIMESTAMP=1322764740813&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 0 | 0.2 | 0.5 | Documentation | Subramanyan??
Beta1 |  |  |  |  | Replace Step.RecordResult property to make model editing less error prone | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=228814&ID_CACHE_NAME=Pluto_p40108189_31674
[5 empty] | Need to eliminate sequence analyzer errors in all models, model plugins and support files | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=313457&ID_CACHE_NAME=Pluto_p40108189_31674
Beta1 | P2 | Pre Review 1 |  |  | [Review] Model Plugins should be able to define callbacks and configuration entry points | http://nippm.natinst.com/itg/web/knta/crt/RequestDetail.jsp?REQUEST_ID=324633&SAVE_DRAFT=N&TIMESTAMP=1322775892657&ID_CACHE_NAME=Pluto_p40108189_31674&IS_EMBEDDED_PAGE=N | 0 | 0 | 4 | 22 | Usability/Cosmetic | Allen |  | yes | Likely to be deferred. Allen noticed a known architectural limitation of TestStand that we had decided to live with when specifying the feature. Would be very nice to fix for Tester OS and Model Plugins in general, but is not an easy problem

## NOTES
2.5 | richocet
15 | portal2
15 | lfd
2.5 | opposing force
2.5 | blue shift
3.99 | hl e2
5 | day of defeat sourcce
46.49
TO TEST
Add top level threads that generates results to serializer tester. One that out lives the root and one that doesn't