## Sheet1
CAR | Assigned to: | Status | Target for Fix | Affect on testing | Description | Internal or Dev | Description of Solution | Jim Action Required
253121 | Allen Piscitello | Open | 2010SP1 | Fails on hebrew systems | CallExecutable bug | Dev | This is not new to 2010. It is unclear if this is just a testcase error or a step type bug; however, no customer has complained about this and at this point in the release we are fixing only critical or extremely low-risk issues. Targeting 2010 SP1 to investigate. | Just wait for fix
229501 | Carlos Gonzalez | Open | 2010SP1 Waiting on LV2011 | failures | Error execting substep 'Create Class Instance' in 'Step-RunInProject' in StepType.seq. | LV Dev | Deferring Rationale for 2010: LabVIEW must fix this issue. This scenario is present in the automated sequence when dealing with projects and reentrant VIs in the batch and parallel models and when unload all modules is called in the middle of a execution. There is not a simple workaround that TestStand can do. | Jim you should skip this failure until LabVIEW fixes this. Update the CAR to say that the skip should be reenabled if for versions of LabVIEW once this is fixed.
251357 | Erik Crank | Open | 2012 | Possible hang | MFC UI crashing or hanging | Dev | The hang is not really a hang but just an extra suspension and the "fix" is to resume execution. | Is there any way for a test to know if it is being run with a specific UI? Maybe you could check the path of the EXE to see if it has MFC in the path and ignore the error. You should add to the CAR to remove the workaround once fixed.
255005 | Jim Carpenter | Open | 2010SP1 | Fails when testing LV UI in LabVIEW | System level Exception running CVI steps that call C or OBJ files when run in the LV UI in the 2010 LabVIEW Development system on 64-bit OS (DEP enabled) | Dev | This is caused by DEP being enabled on LabVIEW EXE. This problem existed in previous versions of TestStand and it's a rare corner case (calling C/OBJ files AND running the LabVIEW UI inside of LabVIEW Dev). We have another CAR 95945 | Use fix from 192078
254826 | Erik Crank | Open | 2010SP1 | Intermittent failures | Seqedit crashes when running sequence that gets sequence call parameter information in parallel | Dev | The automated tests reported an error when running a sequence call API test sequence in the batch model. I investigated a little and reproduced a crash or run-time error by running the Loop sequence in the attached sequence file. The sequence only gets information about parameters and does not set any properties so it should be safe to call in parallel. | Fixed in 2010 SP1
255127 | Jeff Atkinson | Open | 2010SP1 | Intermittent failures | Need to update 4.5\API\DotNet.seq to eliminate false positives | Internal | From Jeff - I can update the automated test when I get some time. I will put in a check to see if VS is installed for the help strings. The other failure is a test that tries to cache the assembly info for randomly selected assemblies in the GAC and verifies that it succeeds. In hindsight I don't think this is a good test because there are too many weird assemblies in the GAC that will fail so I think I will just remove it. We shouldn't skip the entire DotNet.seq file though... | Just wait for fix
251845 | Jim Carpenter | Open | 2010SP1 | Need to reproduce - James may have fixed 10/12 P4 4136242 | Hang on a step that checks if the variable view holds on to a reference improperly | Internal | This seems to be a timing issue with the test software that we have not seen since. James believes it is a autotest issue | See if you can fix timing issue
248353 | Jim Carpenter | Open | A fix was put in place. Monitoring for more failures | Intermittent failures | Calling regsvr32.exe in parallel can sometimes cause errors | Internal | Added a lock to the following sequence that calls regsvr32.exe. edit //TestStand/Tests/Utils/TSTestUtil/TSTestUtil_3.5.seq#16 Change 4127329 submitted. | A fix was put in place. Monitoring for more failures
253234 | Jim Carpenter | Open | 2010SP1 | Fails when testing LV UI in LabVIEW | Bad path when launching LabVIEW UI's. | Internal | Jim state that although this is causing an automated test error, he can work around it. This is purely an internal test SW problem to tackle after release.
256000 | Jim Carpenter | Open | 2010SP1 | Intermittent failures on slow PC's | Timing issue with two sequences | Internal | When run stand alone it passes at 0.05 seconds and the limit is .15 I had an intermittent non-reproducable failure where it took 0.49 seconds to complete. We need to look at how to make it more reliable. It's possible that WIndows is interupting the test momentarilly.
254532 | Jim Carpenter | Open | 2010SP1 | Hang after 4.2 tests on foreign OS's | Unable to install Python using the TestStandAutoTestService on Win 7 x64 German | Internal | Need to investigate
244045 | Jim Carpenter | Open | 2010SP1 | Fails on foreign OS's | CompareReports sequence in TSTestUtil_3.5.seq does not work correctly on Korean OS (and Chinese OS) | Internal | We need to fix the CompareReports sequence. See the attached sequence file that has the fix implemented. The first 4 .NET steps in that sequence replaces all of the Skipped steps. Do the following: 1. Remove all the extraneous steps in CompareReports. 2. Remove unused locals in CompareReports. 3. Remove the TSRegExpr.cpp file from the TSTestUtil.vcproj project and rebuild TSTestUtil.dll. I'm assuming we don't need regular expressions elsewhere in the test suite. Search for RegExpr_ in all test files to verify. If we do, then we should replace them with .NET steps.
256380 | Jim Carpenter | Open | 2010SP1 | Intermittent failure | [Cannot reproduce] [Automated Test] Intermittent failure in MajikEventsTest.seq | ? | Deferring Rationale for 2010: Althought we have not seen this issue before, James expects that this error is just a timing issue for the testcase and not a real bug. We do not have time to investigate this further before 2010 must release.
130303 | Jose Hernandez | Closed | 2010SP1 | Fails on pre-2009SP1 versions of LabVIEW on foreign OS's | The way we are passing binary strings to and from labview in the labview adapter does not work with multi-byte language settings | Internal | Three possible solutions: 1. Modify the autotest based on the language and LabVIEW version. 2. Finish the utility that captures failure patterns and filter the failures through the utility. 3. Update the foreign OS images to only test 2009SP1 and up. | Should we skip this test for pre-2009 SP1 versions of LabVIEW?
191612 | Jose Hernandez | Open | Won't be fixed | Fails when testing LV UI in LabVIEW | GAdapter\arraytest.seq test fails when run with the UI in LabVIEW because the LV controls have the same name | Dev | Deferring Rationale for 2010: This is not a new issue, we just happened to hit this now that we have improved our matrix of autotests with various LabVIEW versions. We have not heard of any customer complaining about this. Note that this can now occur out of the box since our default UI is now built with 8.6.1, but in the end customers almost always recompile our UIs. We do not expect many customers will see this; they typically do not use these TS API constants in their tests and their UI and test VIs are usually compiled with the same LabVIEW version. We will KIL this issue. | Jim you should skip this failure until we fix it. Update the CAR to say that the skip should be reenabled if for versions of TS once this is fixed.
256192 | Jose Hernandez | Open | 2010SP1 | Fails intermittently on mb OS's | Test fails on a chinese image because of AM / PM timestamp comparision issue | Internal | Test fails on a chinese image because of the AM / PM timestamp. Jose looked at the failure and concluded it was the am / pm timestamp causing the failures. I changed the timestamp to AM and the test passes. | Jim you should skip this failure until Erik fixes this. Update the CAR to say that the skip should be reenabled for versions of TS once this is fixed.
239286 | Scott Richardson | Open | 2010SP1 | failures | 2.0 tests multiple IVI failures | Internal | Modify the test sequence to create the ivi session using the class step type instead of the tools step type. | Wait for fix.
254058 | Scott Richardson | Open | 2010SP1 | Need to reboot xfiles and retest | Intermittent unhandled exception | Internal | Re-boot xfiles to continue testing | Wait for fix.